Pera, Blessly R.

BSIT 4-3

Project Management


Assignment:

- Organize and event following the nine elements of project management.

Event Title:

- Blanca’s 18th Birthday Party

Project Background:

- This project intends to organize a birthday party (debut) for a family member and to achieve the milestones or goals on or before the party.

Project Objective:

- To organize a birthday party for a family member within six weeks and not to exceed ₱85,000.

Project Management Integration:

Scope:

The scope of the party are the following:

- The party must held in a resort.

- Invitations are all sent week before the party.

- The food and drinks must be provided by a catering service and chosen according to the debutant’s preference.

- The party must start at 6pm and end at 3am.

- Set-up decoration must be all set before 6pm.

Cost:

Budget: ₱85, 000.00

Time:

| 1ST WEEK | 2ND WEEK | 3RD WEEK | 4TH WEEK | 5TH WEEK | 6TH WEEK |
| --- | --- | --- | --- | --- | --- |
| START Finding and acquiring a reservation in a resort | Finding and booking a catering service and food tasting | Guests listing Program planning Find and book a reservation for lights and sounds system | Creating and designing the invitations Purchase souvenirs | Distribution of the invitations Renting tables and chairs | Set-up decorations for the event Distribution of souvenirs EVENT PROPER |

Quality:

  - No alcoholic beverages are to be served.

  - All guests must attend.

  - Food must be enough for all the guests.

  - Security of the guests are assured.

Human Resource:

Procurement:

| Procured Item / Service | Debit | Credit |
| --- | --- | --- |
| Food Expense |  |  |
| Catering Service | 20, 000.00 | 20, 000.00 |
| Materials Expense |  |  |
| Souvenirs Expense | 15, 000.00 | 15, 000.00 |
| Invitations Expense | 5, 000.00 | 5, 000.00 |
| Venue Rent Expense | 20, 000.00 | 20, 000.00 |
| Equipment Rent Expense | 20, 000.00 | 20, 000.00 |
| Total | 80, 000.00 | 80,000.00 |

| Total Expense | 80, 000.00 |  |
| --- | --- | --- |
| Budget |  | 85, 000.00 |
| Remaining Balance | 5, 000.00 |  |

Risk Management:

- Delays in the delivery of equipment and decoration.

- The weather might hinder the event.

- The food might not be enough for the guests

- Accidents are possible during the party.

Communication:

- The communication method used is active and passive which means it has face-to-face meetings, telephone conversations, e-mails and sms.